## Sheet1
Stakeholder Group | Awareness | Desire | Knowledge | Ability | Reinforcement | Key Risk | Mitigation Action
Customers | Medium Risk: The impacts of the delays in customer service are felt by the customers, but they have no way of knowing that this change will resolve that | Medium Risk: Customers may prefer in-person interactions when dealing with complicated or important matters like their finances and debt. | Low Risk: Customers won't know how to use the new portal and will require supporting resources | Low Risk: Customers unable to use online infrastructure | High Risk: Initial issues or errors with their important information will lead to large, severe distrust | Reinforcement: Initial problems regarding sensitive and important information could lead to permanent trust damage. | Rigorous final product testing pre roll-out.
Collections Representatives | Low Risk: Respresentatives may not see how a self-serve portal helps with specific personal time sinks like double-entry | Medium Risk: Representatives may fear job losses if the system is too effective | High Risk: Representatives may be resistant to retraining with a new portal, especially those with their own existing workarounds | Low Risk | Medium Risk: Initial teething problems, or slowing of processes will lead people to prefer their existing methods | Knowledge: Many employees have existing workarounds and may be reluctant to try new methods / portals | Present to representatives around the new methods, emphasising the benefits
Management (Gareth) | Low Risk: May not be immediately obvious how this improves transparency around representative time use. | Medium Risk: An oversimplified system that ultimately leads to more errors or work would be worse than the current one | Low Risk | Low Risk | Medium risk: Missed complexities that arise later on could derail the sytem, such as edge case escalation pathways | Desire: If the system doesn't contain the appropriate level of complexity, Gareth will not be willing to buy in | Check to-be processes with Graham to ensure complexity is sufficient and known edge cases and escalations are accounted for
Finance (Daniel) | Low Risk | High Risk: If clear financial benefits and trade-offs are not presented, the proposal will be rejected | Low Risk | Medium Risk: A proposal with too large a scope may be impossible to implement financially. | Low Risk | Desire: if the financial benefits aren't clear and the proposal doesn't clearly articulate its trade-offs, the finances will not be granted | Check final presentation with stakeholder to ensure it is suitable for senior leadership to defend the idea
Compliance (Daniel) | Low Risk: May not be obvious how the self-serve portal improves informational transparency and consistency | High Risk: Giving customers more control over their options may lead to opportunities for exploitation / errored plan offerings, that fail regulatory requirements. | Low Risk: Different data security regulations may apply | Low Risk | Low Risk | Desire: If the system is not rigorously crafted to avoid manipulation by bad-actors, it will not be compliant and not be approved. | Rigorous final product testing pre roll-out.
Product Manager (Priya) | Low Risk | Low Risk | Low Risk | Low Risk | Medium Risk: Lack of scalability could lead to later abandonment, as opposed to the desired buildable thinking | Reinforcement: If the system is not scalable, the project will be a failure | Build in scalability by being flexible in data storage, server hosting, and other attributes. This will allow scalability of traffic and greater compliance with potential changes to other internal systems.